## Gimli & Vader
| GIMLI |  |  |  | VADER
Sl no. | Tasks |  |  | Sl no. | Tasks
1 | Datasheet conversion to xml and update in device file | 2023-10-16 |  | 1 | Datasheet conversion to xml and update in device file | 2023-11-15
2 | Device file creation |  |  | 2 | Device file creation
3 | AppConfig updation |  |  | 3 | AppConfig updation
4 | Plugin creation and Add Adaptercontrol and registercontrol plugins |  |  | 4 | Plugin creation and Add Adaptercontrol and registercontrol plugins
5 | Mapping registers with Device tab GUI | 2023-10-25 |  | 5 | Device tab & Protocol tab GUI creation | 2023-11-22
6 | Device tab GUI creation | 2023-11-03 |  | 6 | Mapping registers with Device tab GUI | 2023-11-29
7 | Formulae adding and code modifications | 2023-11-10 | Beta | 7 | OTP access code modifications (formulae including) | 2023-12-13 | Beta
8 | Testing device in virtual mode & Installer package development | 2023-11-16 |  | 8 | Testing with virtual device & Installer package development | 2023-12-20
Total | Estimated date | 2023-11-16 |  | Total | Estimated date | 2023-12-20